## SRR
Beyond Empower - Strategic Risk Register
April 2021
Risk Ref No | Risk Lens | Risk Detail |  |  | Risk Owner | Current Imp x Prob | Key Control Measures | Current Month |  |  | Related KPIs | Risk Appetite (From March 20201) | Net Risk Score Within Risk Appetite? (Y/N) (March 2020) | Actions Required To Bring Towards Target | Actions completion Date | Progress update for Board meeting | Three Lines of Defence |  |  | Overall Strength of Assurnance (high, Medium, Low) | Target Risk
|  | Risk | Cause | Consequence |  | DATE # |  | Impact | Prob | Total | [6 empty] | Management Oversight | Board oversight | External |  | Impact | Prob | Total
G1 | Our Governance | Our core governance arrangements are not robust in all areas | Do not have clearly defined framework of governance, roles and decision-making or oversight of risks. Inadequate capacity and skills. Inadequate non-executive input and scrutiny. | Poor decision making. Risks to company not duly considered. Do not meet expectations of commisisoners and fail to win business. Do not meet expectations of Regulator. Miss filing deadlines with Companies house/CIC Regulator | Board & MD
G2 | Our Governance | There is a lack of vision and strategic and operational planning | Abense of agreed vision and plans. | X drifts and misses opportunities for growth. Future sustaintability compromised. | Board & MD
SU1 | Our Service Users | Desired servcie user outcomes and benefits not realised and expectations of Commssioners not realised | Lack of leadership and investment in staff. Quality of service and engagement not appropriiate. Skills of Lifestyle Coaches not at right level and quality | Poor service outcomes. Risk that contracts not renewed/extended. Do not attract/win new commisisons. Poor reputation. | MD
SU2 | Our Service Users | Do not meet health & safety responsibilities and safeguarding standards | Any breach of requirements. Policies, procedures and reporting not adequate or complied with. Poor induction. | Harm to indivduals Recruitment & retention issues. Adverse comments from Commissioners. Reputational damage | MD & Lifecoachs
F1 | Our Finances | Lack of longer term financial sustainability/security | Dependency on 2 main commisions that run out in Dec 23 and Mar 24. | If new contracts or income streams not secured the CIC cannot survive resulting in loss of services to disabled people and loss of jobs | Board & MD
F2 | Our Finances | Our financial management & control arrangements are not robust | Shortfall in capacity & skills. Standard financial systems not implemented. Poor policies, procedures and reporting. | Uncertainty to overall financial position in-year and future years, cash flow forecasting and propriety over transactions. Income not collected. Unforseen overspend/defict and financial crisis. Other losses. Adverse audit commentary. Miss filing deadlines with Companies house and CIC Regulator. | Board & MD
P1 | Our People | Signifcant dependency on MD and lack of cover for small number of employees | Business start up. | Cannot deliver against plans & expectations. Falling standards. Reputational damange | Board & MD
P2 | Our People | Unable to attract new staff to fill vacancies and/or as the company grows | Small Business start up without a track record | Cannot deliver against plans & expectations. Falling standards. Reputational damange | Board & MD
O1 | Our operations | Loss of individual IT assets | Lack of care and diligence in keeping IT safe. Theft | Loss of data. GDPR breach. Financial loss. Prosecution by ICO and fine. | All
O2 | Our operations | IT infrastructure doesn't effectively support company. | Lack of integrated and up to date arrangements. | Inefficiencies. IT outage. Poor records. Risk of poor data quality or loss. License breaches | MD
O3 | Our operations | Suffer serious disruption to business activities due to: loss of staff, ill-health, loss of data and systems, loss of use of premises or office space | Arrangements for disaster recovery and business continuity not fit for purpose or not in place. | Cannot deliver services. Loss of access to space/premises. Employees cannot access records. No access to payroll or financial processes. Reputaional damage. | MD
R1 | Our regulatory & legal compliance | Do not comply with the requirements of GDPR & Data Protection Act 2018 | Any breach. Lack of understanding of personal responsibilities regulations. Policies not in place and understood and & complied with. Insufficient IT security . | Breach of GDPR regulations and financial fine. Data loss. Systems compromised. Prosecution. Reputational damage. | Board & MD
R2 | Our regulatory & legal compliance | Do not effectively discharge respsonsibilities for Health & Safety and Safeguarding resulting in non-compliance. | Any breach. Lack of understanding of personal responsibilities regulations. Policies not in place and understood and & complied with.. | Harm to users, staff, contractors. Litigation/Prosecution. Financial loss.Reputational damage. Closure of company/sustainability issues. | Board & MD
C1 | Our Communities & Environment | Inappropriate or inadequate engagement with wider community and stakeholders. | Lack of protocol and clear strategy. | Reputational damage. Missed opportunities for wider social impact and potential funding streams. | MD
C2 | Our Communities & Environment | Do not meet social and environmental responsibilities | Lack of clear expectations and buy in | Reputational damage. Missed opportunities for wider social impact and potential funding streams. Not environmentally friendly. | MD
B1 | Our growth & new business | Opportunities for growth and securing new funding streams are missed. | Do not have a clear strategy and plan for growth. Do not effectively engage and promote business. | Future sustainability compromised. Do not achieve economies of scale. | MD
| Financial (based on £xM Turnover) | Reputational, Infrastructure, Sector
IMPACT | Greater than 50% of expected surplus | Catastrophic | 5 | 5 | 10 | 15 | 20
| 25 -50% of expected surplus | Major | 4 | 4 | 8 | 12 | 16
| 10-24% of expected surplus | Moderate | 3 | 3 | 6 | 9 | 12
| 5-9% of expected surplus | Minor | 2 | 2 | 4 | 6 | 8
| <5% of expected surplus | Insignificant | 1 | 1 | 2 | 3 | 4
|  |  |  | 1 | 2 | 3 | 4
|  |  |  | Rare | Unlikely | Possible | Likely
|  |  |  | < 1% chance | 1-10% chance | 10-50% chance | 50-90% chance
Probability
-All required documentation in place and complied with.
- Business plan and strategy finalised.
- Vision and values agreed.
- Monitoring against commissioner requirements in place
-User outcomes defined & assessed
- Social Impact approach in place.
- Business assisstant in place.
- 6 monthly/ annual review of control framweork by Board
-Regular reports to Board
-19/20 accounts filed with Companies house, 20/21 in hand
-Polices in place.
-Compliments & compliants captured.
-Incidents captured
- Financial forecast
-Net profit %
-Reserves built up to meet policy
- New substantive contracts secured no later than late 2022
- Business Continuity plan and actions in place.
- Cover in place
-Staff benefit policy in place
-Staff learning & development undertaken
-Level & quality of responses when recruiting
- No incidents happened & recorded
- No outage or down time
-Business continuity and disaster recovery plan in place.
-Demonstration of ability to recover
- No incidents happended & recorded
- No incidents happended & recorded
- Feedback received
- Resposnses to surveys
- Meeting any agreed targets
- Identified business plan and growth targets met

## Risk Scoring Matrix
| Financial (based on £xM Turnover) | Reputational, Infrastructure, Sector | [7 empty] | Financial (based on £xM Turnover) | Reputational, Infrastructure, Sector
IMPACT | Greater than 50% of expected surplus | Catastrophic | 5 | 5 | 10 | 15 | 20 | 25 | IMPACT | Greater than 50% of expected surplus | Catastrophic | 5
| 25 -50% of expected surplus | Major | 4 | 4 | 8 | 12 | 16 | 20 |  | 25 -50% of expected surplus | Major | 4
| 10-24% of expected surplus | Moderate | 3 | 3 | 6 | 9 | 12 | 15 |  | 10-24% of expected surplus | Moderate | 3
| 5-9% of expected surplus | Minor | 2 | 2 | 4 | 6 | 8 | 10 |  | 5-9% of expected surplus | Minor | 2
| <5% of expected surplus | Insignificant | 1 | 1 | 2 | 3 | 4 | 5 |  | <5% of expected surplus | Insignificant | 1
|  |  |  | 1 | 2 | 3 | 4 | 5 |  |  |  |  | 1 | 2 | 3 | 4 | 5
|  |  |  | Rare | Unlikely | Possible | Likely | Almost Certain |  |  |  |  | Rare | Unlikely | Possible | Likely | Almost Certain
|  |  |  | < 1% chance | 1-10% chance | 10-50% chance | 50-90% chance | >90% chance |  |  |  |  | < 1% chance | 1-10% chance | 10-50% chance | 50-90% chance | >90% chance
|  |  |  | Probability | [8 empty] | Probability
To update | [8 empty] | Heat map
To update in accordance with Risk Management Strategy | [8 empty] | Risks ref numbers will be shown in appropriate cell to provide Heat Map